## BALUYUT, RANZ JONNEL (hidden)
TASK NO. | TASK NAME | DURATION
1 | AAA | 1 |  | 0 |  | 1
2 | BBB | 3 |  | es |  | ef
3 | CCC | 1 |  | AAA |  |  |  |  | III |  | QQQ | [6 empty] | EARLIEST |  | LATEST
4 | DDD | 5 |  | 1 | 0 | 1 |  |  | 9 |  | 17 |  |  |  | TASK | DURATION | PREDECESSOR | ES | EF | LS | LF | TOTAL SLACK
5 | EEE | 2 | ls | 0 |  | 1 | lf | EEE |  | MMM |  | UUU |  |  | AAA | 1 | - | 0 | 1 | 0 | 1 | 0
6 | FFF | 8 | [5 empty] | 5 |  | 13 |  | 21 |  |  | BBB
7 | GGG | 6 |  | BBB |  |  |  |  | JJJ |  | RRR |  | XXX |  | CCC
8 | HHH | 4 |  | 2 |  |  |  |  | 10 |  | 18 |  | 24 |  | DDD
9 | III | 6 | [5 empty] | FFF |  | NNN |  | VVV |  | ZZZ | EEE
10 | JJJ | 4 | [5 empty] | 6 |  | 14 |  | 22 |  | 26 | FFF
11 | KKK | 6 |  | CCC |  |  |  |  | KKK |  | SSS |  | YYY |  | GGG
12 | LLL | 3 |  | 3 |  |  |  |  | 11 |  | 19 |  | 25 |  | HHH
13 | MMM | 9 | [5 empty] | GGG |  | OOO |  | WWW |  |  | III
14 | NNN | 6 | [5 empty] | 7 |  | 15 |  | 23 |  |  | JJJ
15 | OOO | 4 |  | DDD |  |  |  |  | LLL |  | TTT |  |  |  | KKK
16 | PPP | 3 |  | 4 |  |  |  |  | 12 |  | 20 |  |  |  | LLL
17 | QQQ | 4 | [5 empty] | HHH |  | PPP |  |  |  |  | MMM
18 | RRR | 5 | [5 empty] | 8 |  | 16 |  |  |  |  | NNN
19 | SSS | 6 | [12 empty] | OOO
20 | TTT | 4 | [12 empty] | PPP
21 | UUU | 4 | [12 empty] | QQQ
22 | VVV | 3 | [12 empty] | RRR
23 | WWW | 5 | [12 empty] | SSS
24 | XXX | 2 | [12 empty] | TTT
25 | YYY | 7 | [12 empty] | UUU
26 | ZZZ | 5 | [12 empty] | VVV
WWW
XXX
YYY
ZZZ

## BUENAVENTURA, CZECH JOSH (hidden)
TASK NO. | TASK NAME | DURATION
1 | AAA | 2
2 | BBB | 3
3 | CCC | 1 | AAA |  | III |  | QQQ | [6 empty] | EARLIEST |  | LATEST
4 | DDD | 5 | 1 |  | 9 |  | 17 |  |  |  | TASK | DURATION | PREDECESSOR | ES | EF | LS | LF | TOTAL SLACK
5 | EEE | 6 |  | EEE |  | MMM |  | UUU |  |  | AAA
6 | FFF | 9 |  | 5 |  | 13 |  | 21 |  |  | BBB
7 | GGG | 1 | BBB |  | JJJ |  | RRR |  | XXX |  | CCC
8 | HHH | 4 | 2 |  | 10 |  | 18 |  | 24 |  | DDD
9 | III | 6 |  | FFF |  | NNN |  | VVV |  | ZZZ | EEE
10 | JJJ | 4 |  | 6 |  | 14 |  | 22 |  | 26 | FFF
11 | KKK | 6 | CCC |  | KKK |  | SSS |  | YYY |  | GGG
12 | LLL | 3 | 3 |  | 11 |  | 19 |  | 25 |  | HHH
13 | MMM | 9 |  | GGG |  | OOO |  | WWW |  |  | III
14 | NNN | 6 |  | 7 |  | 15 |  | 23 |  |  | JJJ
15 | OOO | 4 | DDD |  | LLL |  | TTT |  |  |  | KKK
16 | PPP | 3 | 4 |  | 12 |  | 20 |  |  |  | LLL
17 | QQQ | 4 |  | HHH |  | PPP |  |  |  |  | MMM
18 | RRR | 5 |  | 8 |  | 16 |  |  |  |  | NNN
19 | SSS | 6 | [8 empty] | OOO
20 | TTT | 4 | [8 empty] | PPP
21 | UUU | 5 | [8 empty] | QQQ
22 | VVV | 3 | [8 empty] | RRR
23 | WWW | 7 | [8 empty] | SSS
24 | XXX | 2 | [8 empty] | TTT
25 | YYY | 11 | [8 empty] | UUU
26 | ZZZ | 5 | [8 empty] | VVV
WWW
XXX
YYY
ZZZ

## CRUZ, KURT (hidden)
TASK NO. | TASK NAME | DURATION
1 | AAA | 2
2 | BBB | 3
3 | CCC | 2 | AAA |  | III |  | QQQ | [6 empty] | EARLIEST |  | LATEST
4 | DDD | 5 | 1 |  | 9 |  | 17 |  |  |  | TASK | DURATION | PREDECESSOR | ES | EF | LS | LF | TOTAL SLACK
5 | EEE | 6 |  | EEE |  | MMM |  | UUU |  |  | AAA
6 | FFF | 8 |  | 5 |  | 13 |  | 21 |  |  | BBB
7 | GGG | 4 | BBB |  | JJJ |  | RRR |  | XXX |  | CCC
8 | HHH | 4 | 2 |  | 10 |  | 18 |  | 24 |  | DDD
9 | III | 6 |  | FFF |  | NNN |  | VVV |  | ZZZ | EEE
10 | JJJ | 4 |  | 6 |  | 14 |  | 22 |  | 26 | FFF
11 | KKK | 6 | CCC |  | KKK |  | SSS |  | YYY |  | GGG
12 | LLL | 8 | 3 |  | 11 |  | 19 |  | 25 |  | HHH
13 | MMM | 12 |  | GGG |  | OOO |  | WWW |  |  | III
14 | NNN | 6 |  | 7 |  | 15 |  | 23 |  |  | JJJ
15 | OOO | 4 | DDD |  | LLL |  | TTT |  |  |  | KKK
16 | PPP | 3 | 4 |  | 12 |  | 20 |  |  |  | LLL
17 | QQQ | 4 |  | HHH |  | PPP |  |  |  |  | MMM
18 | RRR | 5 |  | 8 |  | 16 |  |  |  |  | NNN
19 | SSS | 6 | [8 empty] | OOO
20 | TTT | 4 | [8 empty] | PPP
21 | UUU | 6 | [8 empty] | QQQ
22 | VVV | 3 | [8 empty] | RRR
23 | WWW | 10 | [8 empty] | SSS
24 | XXX | 2 | [8 empty] | TTT
25 | YYY | 7 | [8 empty] | UUU
26 | ZZZ | 5 | [8 empty] | VVV
WWW
XXX
YYY
ZZZ

## GARCIA, FRANZ JOSEPH (hidden)
TASK NO. | TASK NAME | DURATION
1 | AAA | 2
2 | BBB | 3
3 | CCC | 1 | AAA |  | III |  | QQQ | [6 empty] | EARLIEST |  | LATEST
4 | DDD | 5 | 1 |  | 9 |  | 17 |  |  |  | TASK | DURATION | PREDECESSOR | ES | EF | LS | LF | TOTAL SLACK
5 | EEE | 6 |  | EEE |  | MMM |  | UUU |  |  | AAA
6 | FFF | 8 |  | 5 |  | 13 |  | 21 |  |  | BBB
7 | GGG | 3 | BBB |  | JJJ |  | RRR |  | XXX |  | CCC
8 | HHH | 4 | 2 |  | 10 |  | 18 |  | 24 |  | DDD
9 | III | 6 |  | FFF |  | NNN |  | VVV |  | ZZZ | EEE
10 | JJJ | 4 |  | 6 |  | 14 |  | 22 |  | 26 | FFF
11 | KKK | 6 | CCC |  | KKK |  | SSS |  | YYY |  | GGG
12 | LLL | 9 | 3 |  | 11 |  | 19 |  | 25 |  | HHH
13 | MMM | 12 |  | GGG |  | OOO |  | WWW |  |  | III
14 | NNN | 6 |  | 7 |  | 15 |  | 23 |  |  | JJJ
15 | OOO | 4 | DDD |  | LLL |  | TTT |  |  |  | KKK
16 | PPP | 3 | 4 |  | 12 |  | 20 |  |  |  | LLL
17 | QQQ | 4 |  | HHH |  | PPP |  |  |  |  | MMM
18 | RRR | 5 |  | 8 |  | 16 |  |  |  |  | NNN
19 | SSS | 6 | [8 empty] | OOO
20 | TTT | 4 | [8 empty] | PPP
21 | UUU | 3 | [8 empty] | QQQ
22 | VVV | 3 | [8 empty] | RRR
23 | WWW | 12 | [8 empty] | SSS
24 | XXX | 2 | [8 empty] | TTT
25 | YYY | 7 | [8 empty] | UUU
26 | ZZZ | 5 | [8 empty] | VVV
WWW
XXX
YYY
ZZZ

## GRAGAS, FRANZ MCKLEIN (hidden)
TASK NO. | TASK NAME | DURATION
1 | AAA | 5
2 | BBB | 3
3 | CCC | 10 | 0 | AAA |  | III |  | QQQ | [6 empty] | EARLIEST |  | LATEST
4 | DDD | 5 |  | 1 |  | 9 |  | 17 |  |  |  | TASK | DURATION | PREDECESSOR | ES | EF | LS | LF | TOTAL SLACK
5 | EEE | 6 |  |  | EEE |  | MMM |  | UUU |  |  | AAA
6 | FFF | 4 |  |  | 5 |  | 13 |  | 21 |  |  | BBB
7 | GGG | 8 |  | BBB |  | JJJ |  | RRR |  | XXX |  | CCC
8 | HHH | 4 |  | 2 |  | 10 |  | 18 |  | 24 |  | DDD
9 | III | 6 |  |  | FFF |  | NNN |  | VVV |  | ZZZ | EEE
10 | JJJ | 4 |  |  | 6 |  | 14 |  | 22 |  | 26 | FFF
11 | KKK | 6 | 0 | CCC |  | KKK |  | SSS |  | YYY |  | GGG
12 | LLL | 12 |  | 3 |  | 11 |  | 19 |  | 25 |  | HHH
13 | MMM | 9 |  |  | GGG |  | OOO |  | WWW |  |  | III
14 | NNN | 6 |  |  | 7 |  | 15 |  | 23 |  |  | JJJ
15 | OOO | 4 |  | DDD |  | LLL |  | TTT |  |  |  | KKK
16 | PPP | 3 |  | 4 |  | 12 |  | 20 |  |  |  | LLL
17 | QQQ | 4 |  |  | HHH |  | PPP |  |  |  |  | MMM
18 | RRR | 5 |  |  | 8 |  | 16 |  |  |  |  | NNN
19 | SSS | 6 | [9 empty] | OOO
20 | TTT | 4 | [9 empty] | PPP
21 | UUU | 5 | [9 empty] | QQQ
22 | VVV | 3 | [9 empty] | RRR
23 | WWW | 10 | [9 empty] | SSS
24 | XXX | 2 | [9 empty] | TTT
25 | YYY | 7 | [9 empty] | UUU
26 | ZZZ | 5 | [9 empty] | VVV
WWW
XXX
YYY
ZZZ

## MANASAN, THOMAS (hidden)
TASK NO. | TASK NAME | DURATION
1 | AAA | 2
2 | BBB | 6
3 | CCC | 1 | 0 | AAA |  | III |  | QQQ | [6 empty] | EARLIEST |  | LATEST
4 | DDD | 5 |  | 1 |  | 9 |  | 17 |  |  |  | TASK | DURATION | PREDECESSOR | ES | EF | LS | LF | TOTAL SLACK
5 | EEE | 6 |  |  | EEE |  | MMM |  | UUU |  |  | AAA
6 | FFF | 8 |  |  | 5 |  | 13 |  | 21 |  |  | BBB
7 | GGG | 12 | 0 | BBB |  | JJJ |  | RRR |  | XXX |  | CCC
8 | HHH | 4 |  | 2 |  | 10 |  | 18 |  | 24 |  | DDD
9 | III | 6 |  |  | FFF |  | NNN |  | VVV |  | ZZZ | EEE
10 | JJJ | 4 |  |  | 6 |  | 14 |  | 22 |  | 26 | FFF
11 | KKK | 8 |  | CCC |  | KKK |  | SSS |  | YYY |  | GGG
12 | LLL | 16 |  | 3 |  | 11 |  | 19 |  | 25 |  | HHH
13 | MMM | 9 |  |  | GGG |  | OOO |  | WWW |  |  | III
14 | NNN | 6 |  |  | 7 |  | 15 |  | 23 |  |  | JJJ
15 | OOO | 4 |  | DDD |  | LLL |  | TTT |  |  |  | KKK
16 | PPP | 3 |  | 4 |  | 12 |  | 20 |  |  |  | LLL
17 | QQQ | 4 |  |  | HHH |  | PPP |  |  |  |  | MMM
18 | RRR | 5 |  |  | 8 |  | 16 |  |  |  |  | NNN
19 | SSS | 6 | [9 empty] | OOO
20 | TTT | 4 | [9 empty] | PPP
21 | UUU | 7 | [9 empty] | QQQ
22 | VVV | 3 | [9 empty] | RRR
23 | WWW | 14 | [9 empty] | SSS
24 | XXX | 2 | [9 empty] | TTT
25 | YYY | 7 | [9 empty] | UUU
26 | ZZZ | 5 | [9 empty] | VVV
WWW
XXX
YYY
ZZZ

## PAGUIO, GARRED ALDANE (hidden)
TASK NO. | TASK NAME | DURATION
1 | AAA | 2
2 | BBB | 3
3 | CCC | 5 | AAA |  | III |  | QQQ | [6 empty] | EARLIEST |  | LATEST
4 | DDD | 5 | 1 |  | 9 |  | 17 |  |  |  | TASK | DURATION | PREDECESSOR | ES | EF | LS | LF | TOTAL SLACK
5 | EEE | 6 |  | EEE |  | MMM |  | UUU |  |  | AAA
6 | FFF | 8 |  | 5 |  | 13 |  | 21 |  |  | BBB
7 | GGG | 10 | BBB |  | JJJ |  | RRR |  | XXX |  | CCC
8 | HHH | 4 | 2 |  | 10 |  | 18 |  | 24 |  | DDD
9 | III | 6 |  | FFF |  | NNN |  | VVV |  | ZZZ | EEE
10 | JJJ | 4 |  | 6 |  | 14 |  | 22 |  | 26 | FFF
11 | KKK | 6 | CCC |  | KKK |  | SSS |  | YYY |  | GGG
12 | LLL | 15 | 3 |  | 11 |  | 19 |  | 25 |  | HHH
13 | MMM | 9 |  | GGG |  | OOO |  | WWW |  |  | III
14 | NNN | 6 |  | 7 |  | 15 |  | 23 |  |  | JJJ
15 | OOO | 4 | DDD |  | LLL |  | TTT |  |  |  | KKK
16 | PPP | 3 | 4 |  | 12 |  | 20 |  |  |  | LLL
17 | QQQ | 4 |  | HHH |  | PPP |  |  |  |  | MMM
18 | RRR | 5 |  | 8 |  | 16 |  |  |  |  | NNN
19 | SSS | 9 | [8 empty] | OOO
20 | TTT | 4 | [8 empty] | PPP
21 | UUU | 6 | [8 empty] | QQQ
22 | VVV | 3 | [8 empty] | RRR
23 | WWW | 12 | [8 empty] | SSS
24 | XXX | 2 | [8 empty] | TTT
25 | YYY | 7 | [8 empty] | UUU
26 | ZZZ | 5 | [8 empty] | VVV
WWW
XXX
YYY
ZZZ

## REGALA, GERALD (hidden)
TASK NO. | TASK NAME | DURATION
1 | AAA | 2
2 | BBB | 3
3 | CCC | 4 | AAA |  | III |  | QQQ | [6 empty] | EARLIEST |  | LATEST
4 | DDD | 5 | 1 |  | 9 |  | 17 |  |  |  | TASK | DURATION | PREDECESSOR | ES | EF | LS | LF | TOTAL SLACK
5 | EEE | 6 |  | EEE |  | MMM |  | UUU |  |  | AAA
6 | FFF | 8 |  | 5 |  | 13 |  | 21 |  |  | BBB
7 | GGG | 16 | BBB |  | JJJ |  | RRR |  | XXX |  | CCC
8 | HHH | 4 | 2 |  | 10 |  | 18 |  | 24 |  | DDD
9 | III | 6 |  | FFF |  | NNN |  | VVV |  | ZZZ | EEE
10 | JJJ | 4 |  | 6 |  | 14 |  | 22 |  | 26 | FFF
11 | KKK | 6 | CCC |  | KKK |  | SSS |  | YYY |  | GGG
12 | LLL | 14 | 3 |  | 11 |  | 19 |  | 25 |  | HHH
13 | MMM | 9 |  | GGG |  | OOO |  | WWW |  |  | III
14 | NNN | 6 |  | 7 |  | 15 |  | 23 |  |  | JJJ
15 | OOO | 4 | DDD |  | LLL |  | TTT |  |  |  | KKK
16 | PPP | 3 | 4 |  | 12 |  | 20 |  |  |  | LLL
17 | QQQ | 4 |  | HHH |  | PPP |  |  |  |  | MMM
18 | RRR | 5 |  | 8 |  | 16 |  |  |  |  | NNN
19 | SSS | 6 | [8 empty] | OOO
20 | TTT | 4 | [8 empty] | PPP
21 | UUU | 12 | [8 empty] | QQQ
22 | VVV | 3 | [8 empty] | RRR
23 | WWW | 10 | [8 empty] | SSS
24 | XXX | 2 | [8 empty] | TTT
25 | YYY | 7 | [8 empty] | UUU
26 | ZZZ | 5 | [8 empty] | VVV
WWW
XXX
YYY
ZZZ

## RICAFORT, RALPH KRISTIAN (hidden)
TASK NO. | TASK NAME | DURATION
1 | AAA | 2 |  | p
2 | BBB | 3
3 | CCC | 9 | 0 | AAA |  |  | III |  | QQQ | [6 empty] | EARLIEST |  | LATEST
4 | DDD | 5 |  | 1 | 2 |  | 9 |  | 17 |  |  |  | TASK | DURATION | PREDECESSOR | ES | EF | LS | LF | TOTAL SLACK
5 | EEE | 6 |  |  |  | EEE |  | MMM |  | UUU |  |  | AAA
6 | FFF | 8 |  |  |  | 5 |  | 13 |  | 21 |  |  | BBB
7 | GGG | 9 |  | BBB |  |  | JJJ |  | RRR |  | XXX |  | CCC
8 | HHH | 4 |  | 2 | 3 |  | 10 |  | 18 |  | 24 |  | DDD
9 | III | 6 |  |  |  | FFF |  | NNN |  | VVV |  | ZZZ | EEE
10 | JJJ | 4 |  |  |  | 6 |  | 14 |  | 22 |  | 26 | FFF
11 | KKK | 6 | 0 | CCC |  |  | KKK |  | SSS |  | YYY |  | GGG
12 | LLL | 15 |  | 3 | 9 |  | 11 |  | 19 |  | 25 |  | HHH
13 | MMM | 9 |  |  |  | GGG |  | OOO |  | WWW |  |  | III
14 | NNN | 6 |  |  |  | 7 |  | 15 |  | 23 |  |  | JJJ
15 | OOO | 4 | 0 | DDD |  |  | LLL |  | TTT |  |  |  | KKK
16 | PPP | 3 |  | 4 |  |  | 12 |  | 20 |  |  |  | LLL
17 | QQQ | 4 |  |  |  | HHH |  | PPP |  |  |  |  | MMM
18 | RRR | 5 |  |  |  | 8 |  | 16 |  |  |  |  | NNN
19 | SSS | 6 | [10 empty] | OOO
20 | TTT | 4 | [10 empty] | PPP
21 | UUU | 13 | [10 empty] | QQQ
22 | VVV | 3 | [10 empty] | RRR
23 | WWW | 11 |  |  |  | S - TINURO | [6 empty] | SSS
24 | XXX | 2 |  |  |  | P - NAKATURO | [6 empty] | TTT
25 | YYY | 7 | [10 empty] | UUU
26 | ZZZ | 5 | [10 empty] | VVV
WWW
XXX
YYY
ZZZ

## SARMIENTO, LANCE HARVEY (hidden)
TASK NO. | TASK NAME | DURATION
1 | AAA | 2 | es | fp | ef
2 | BBB | 3 | 0 |  | 2
3 | CCC | 1 | AAA |  |  |  |  | III |  | QQQ | [6 empty] | EARLIEST |  | LATEST
4 | DDD | 5 | 1 | 0 | 2 |  |  | 9 |  | 17 |  |  |  | TASK | DURATION | PREDECESSOR | ES | EF | LS | LF | TOTAL SLACK
5 | EEE | 6 | 0 | sl | 2 | EEE |  |  | MMM |  | UUU |  |  | AAA |  |  | 0 | 2 | 0 | 2 | 0
6 | FFF | 8 | ls |  | lf | 5 |  |  | 13 |  | 21 |  |  | BBB
7 | GGG | 4 | BBB |  |  |  |  | JJJ |  | RRR |  | XXX |  | CCC
8 | HHH | 4 | 2 |  |  |  |  | 10 |  | 18 |  | 24 |  | DDD
9 | III | 6 |  |  |  | FFF |  |  | NNN |  | VVV |  | ZZZ | EEE
10 | JJJ | 4 |  |  |  | 6 |  |  | 14 |  | 22 |  | 26 | FFF
11 | KKK | 6 | CCC |  |  |  |  | KKK |  | SSS |  | YYY |  | GGG
12 | LLL | 8 | 3 |  |  |  |  | 11 |  | 19 |  | 25 |  | HHH
13 | MMM | 9 |  |  |  | GGG |  |  | OOO |  | WWW |  |  | III
14 | NNN | 6 |  |  |  | 7 |  |  | 15 |  | 23 |  |  | JJJ
15 | OOO | 4 | DDD |  |  |  |  | LLL |  | TTT |  |  |  | KKK
16 | PPP | 3 | 4 |  |  |  |  | 12 |  | 20 |  |  |  | LLL
17 | QQQ | 4 |  |  |  | HHH |  |  | PPP |  |  |  |  | MMM
18 | RRR | 5 |  |  |  | 8 |  |  | 16 |  |  |  |  | NNN
19 | SSS | 6 | [11 empty] | OOO
20 | TTT | 4 | [11 empty] | PPP
21 | UUU | 12 | [11 empty] | QQQ
22 | VVV | 3 | [11 empty] | RRR
23 | WWW | 16 | [11 empty] | SSS
24 | XXX | 2 | [11 empty] | TTT
25 | YYY | 7 | [11 empty] | UUU
26 | ZZZ | 5 |  |  | forward pass |  | backward pass | [6 empty] | VVV
[5 empty] | earliest start |  | latest start | [6 empty] | WWW
[5 empty] | earliest finish |  | latest finish | [6 empty] | XXX
YYY
ZZZ

## Sheet1 (hidden)
hero section |  | predecessor
navigation
hero title
hero image
hero btn
services
specialty
about
about content
about img
footer
footer links
footer author
animation
hero section
services
about
footer
milestones
hero completed |  | 5
services start |  | 7ss
services completed |  | 7
about

## TICSAY, KINJAY (hidden)
TASK NO. | TASK NAME | DURATION
1 | AAA | 2
2 | BBB | 3
3 | CCC | 5 | AAA |  | III |  | QQQ | [6 empty] | EARLIEST |  | LATEST
4 | DDD | 5 | 1 |  | 9 |  | 17 |  |  |  | TASK | DURATION | PREDECESSOR | ES | EF | LS | LF | TOTAL SLACK
5 | EEE | 6 |  | EEE |  | MMM |  | UUU |  |  | AAA
6 | FFF | 8 |  | 5 |  | 13 |  | 21 |  |  | BBB
7 | GGG | 10 | BBB |  | JJJ |  | RRR |  | XXX |  | CCC
8 | HHH | 4 | 2 |  | 10 |  | 18 |  | 24 |  | DDD
9 | III | 6 |  | FFF |  | NNN |  | VVV |  | ZZZ | EEE
10 | JJJ | 4 |  | 6 |  | 14 |  | 22 |  | 26 | FFF
11 | KKK | 6 | CCC |  | KKK |  | SSS |  | YYY |  | GGG
12 | LLL | 15 | 3 |  | 11 |  | 19 |  | 25 |  | HHH
13 | MMM | 9 |  | GGG |  | OOO |  | WWW |  |  | III
14 | NNN | 6 |  | 7 |  | 15 |  | 23 |  |  | JJJ
15 | OOO | 4 | DDD |  | LLL |  | TTT |  |  |  | KKK
16 | PPP | 3 | 4 |  | 12 |  | 20 |  |  |  | LLL
17 | QQQ | 4 |  | HHH |  | PPP |  |  |  |  | MMM
18 | RRR | 5 |  | 8 |  | 16 |  |  |  |  | NNN
19 | SSS | 6 | [8 empty] | OOO
20 | TTT | 4 | [8 empty] | PPP
21 | UUU | 12 | [8 empty] | QQQ
22 | VVV | 3 | [8 empty] | RRR
23 | WWW | 14 | [8 empty] | SSS
24 | XXX | 2 | [8 empty] | TTT
25 | YYY | 7 | [8 empty] | UUU
26 | ZZZ | 5 | [8 empty] | VVV
WWW
XXX
YYY
ZZZ

## VINO, HADRIAN (hidden)
TASK NO. | TASK NAME | DURATION
1 | AAA | 3
2 | BBB | 6
3 | CCC | 5 | AAA |  | III |  | QQQ | [6 empty] | EARLIEST |  | LATEST
4 | DDD | 5 | 1 |  | 9 |  | 17 |  |  |  | TASK | DURATION | PREDECESSOR | ES | EF | LS | LF | TOTAL SLACK
5 | EEE | 6 |  | EEE |  | MMM |  | UUU |  |  | AAA
6 | FFF | 8 |  | 5 |  | 13 |  | 21 |  |  | BBB
7 | GGG | 9 | BBB |  | JJJ |  | RRR |  | XXX |  | CCC
8 | HHH | 4 | 2 |  | 10 |  | 18 |  | 24 |  | DDD
9 | III | 6 |  | FFF |  | NNN |  | VVV |  | ZZZ | EEE
10 | JJJ | 4 |  | 6 |  | 14 |  | 22 |  | 26 | FFF
11 | KKK | 6 | CCC |  | KKK |  | SSS |  | YYY |  | GGG
12 | LLL | 12 | 3 |  | 11 |  | 19 |  | 25 |  | HHH
13 | MMM | 9 |  | GGG |  | OOO |  | WWW |  |  | III
14 | NNN | 6 |  | 7 |  | 15 |  | 23 |  |  | JJJ
15 | OOO | 4 | DDD |  | LLL |  | TTT |  |  |  | KKK
16 | PPP | 3 | 4 |  | 12 |  | 20 |  |  |  | LLL
17 | QQQ | 4 |  | HHH |  | PPP |  |  |  |  | MMM
18 | RRR | 5 |  | 8 |  | 16 |  |  |  |  | NNN
19 | SSS | 6 | [8 empty] | OOO
20 | TTT | 4 | [8 empty] | PPP
21 | UUU | 15 | [8 empty] | QQQ
22 | VVV | 3 | [8 empty] | RRR
23 | WWW | 18 | [8 empty] | SSS
24 | XXX | 2 | [8 empty] | TTT
25 | YYY | 7 | [8 empty] | UUU
26 | ZZZ | 5 | [8 empty] | VVV
WWW
XXX
YYY
ZZZ

## MANALANG, KIMBERLY (hidden)
TASK NO. | TASK NAME | DURATION
1 | AAA | 2
2 | BBB | 3
3 | CCC | 1 | AAA |  | III |  | QQQ | [6 empty] | EARLIEST |  | LATEST
4 | DDD | 5 | 1 |  | 9 |  | 17 |  |  |  | TASK | DURATION | PREDECESSOR | ES | EF | LS | LF | TOTAL SLACK
5 | EEE | 6 |  | EEE |  | MMM |  | UUU |  |  | AAA
6 | FFF | 4 |  | 5 |  | 13 |  | 21 |  |  | BBB
7 | GGG | 8 | BBB |  | JJJ |  | RRR |  | XXX |  | CCC
8 | HHH | 4 | 2 |  | 10 |  | 18 |  | 24 |  | DDD
9 | III | 6 |  | FFF |  | NNN |  | VVV |  | ZZZ | EEE
10 | JJJ | 4 |  | 6 |  | 14 |  | 22 |  | 26 | FFF
11 | KKK | 6 | CCC |  | KKK |  | SSS |  | YYY |  | GGG
12 | LLL | 12 | 3 |  | 11 |  | 19 |  | 25 |  | HHH
13 | MMM | 9 |  | GGG |  | OOO |  | WWW |  |  | III
14 | NNN | 6 |  | 7 |  | 15 |  | 23 |  |  | JJJ
15 | OOO | 4 | DDD |  | LLL |  | TTT |  |  |  | KKK
16 | PPP | 3 | 4 |  | 12 |  | 20 |  |  |  | LLL
17 | QQQ | 4 |  | HHH |  | PPP |  |  |  |  | MMM
18 | RRR | 5 |  | 8 |  | 16 |  |  |  |  | NNN
19 | SSS | 6 | [8 empty] | OOO
20 | TTT | 4 | [8 empty] | PPP
21 | UUU | 16 | [8 empty] | QQQ
22 | VVV | 3 | [8 empty] | RRR
23 | WWW | 5 | [8 empty] | SSS
24 | XXX | 2 | [8 empty] | TTT
25 | YYY | 7 | [8 empty] | UUU
26 | ZZZ | 5 | [8 empty] | VVV
WWW
XXX
YYY
ZZZ

## ARCILLAS, CAREN JOYCE (hidden)
TASK NO. | TASK NAME | DURATION
1 | AAA | 2
2 | BBB | 3
3 | CCC | 1 | AAA |  | III |  | QQQ | [6 empty] | EARLIEST |  | LATEST
4 | DDD | 5 | 1 |  | 9 |  | 17 |  |  |  | TASK | DURATION | PREDECESSOR | ES | EF | LS | LF | TOTAL SLACK
5 | EEE | 6 |  | EEE |  | MMM |  | UUU |  |  | AAA
6 | FFF | 8 |  | 5 |  | 13 |  | 21 |  |  | BBB
7 | GGG | 15 | BBB |  | JJJ |  | RRR |  | XXX |  | CCC
8 | HHH | 4 | 2 |  | 10 |  | 18 |  | 24 |  | DDD
9 | III | 6 |  | FFF |  | NNN |  | VVV |  | ZZZ | EEE
10 | JJJ | 4 |  | 6 |  | 14 |  | 22 |  | 26 | FFF
11 | KKK | 6 | CCC |  | KKK |  | SSS |  | YYY |  | GGG
12 | LLL | 11 | 3 |  | 11 |  | 19 |  | 25 |  | HHH
13 | MMM | 9 |  | GGG |  | OOO |  | WWW |  |  | III
14 | NNN | 6 |  | 7 |  | 15 |  | 23 |  |  | JJJ
15 | OOO | 4 | DDD |  | LLL |  | TTT |  |  |  | KKK
16 | PPP | 3 | 4 |  | 12 |  | 20 |  |  |  | LLL
17 | QQQ | 4 |  | HHH |  | PPP |  |  |  |  | MMM
18 | RRR | 5 |  | 8 |  | 16 |  |  |  |  | NNN
19 | SSS | 6 | [8 empty] | OOO
20 | TTT | 4 | [8 empty] | PPP
21 | UUU | 10 | [8 empty] | QQQ
22 | VVV | 3 | [8 empty] | RRR
23 | WWW | 12 | [8 empty] | SSS
24 | XXX | 2 | [8 empty] | TTT
25 | YYY | 7 | [8 empty] | UUU
26 | ZZZ | 5 | [8 empty] | VVV
WWW
XXX
YYY
ZZZ

## FIN ACT-2
this is a sample template
| 0 | 1 | [5 empty] | 11 | 14 |  |  |  | 25 |  | 26
| AAA | [6 empty] | III |  |  |  |  | QQQ
| 1 | 1 | 3 |  | 5 |  |  | 0 | 3 | 16 | 18 |  | 0 |  | 1 |  |  | 27 | 28
| 1 | 2 | EEE |  |  |  |  | 11 | 14 | MMM |  |  | 25 |  | 26 |  |  | UUU
| 1 | 2 | 0 |  | 2 |  |  | 14 | 16 | 0 | 2 |  | 26 |  | 27 |  |  | 0 | 1 | 30 |  | 31
| BBB |  | 3 |  | 5 |  |  | JJJ |  | 16 | 18 |  | RRR |  |  |  |  | 27 | 28 | XXX
| 1 | 1 | 5 |  | 7 |  |  | 0 | 2 | 18 | 20 |  | 0 |  | 1 |  |  | 28 | 29 | 0 |  | 1 | 32 |  | 39
| 2 | 3 | FFF |  |  |  |  | 14 | 16 | NNN |  |  | 26 |  | 27 |  |  | VVV |  | 30 |  | 31 | ZZZ
| 0 | 1 | 0 |  | 2 |  |  | 10 | 11 | 0 | 2 |  | 22 |  | 23 |  |  | 0 | 1 | 31 |  | 32 | 0 |  | 7
| CCC |  | 5 |  | 7 |  |  | KKK |  | 18 | 20 |  | SSS |  |  |  |  | 28 | 29 | YYY |  |  | 32 |  | 39
| 0 | 1 | 7 |  | 10 |  |  | 4 | 1 | 20 | 22 |  | 2 |  | 1 |  |  | 29 | 30 | 0 |  | 1
| 0 | 1 | GGG |  |  |  |  | 14 | 15 | OOO |  |  | 24 |  | 25 |  |  | WWW |  | 31 |  | 32
| 1 | 3 | 0 |  | 3 |  |  | 11 | 12 | 0 | 2 |  | 25 |  | 27 |  |  | 0 | 1
| DDD |  | 7 |  | 10 |  |  | LLL |  | 20 | 22 |  | TTT |  |  |  |  | 29 | 30
| 0 | 2 | 10 |  | 11 |  |  | 4 | 1 | 22 | 25 |  | 0 |  | 2
| 1 | 3 | HHH |  |  |  |  | 15 | 16 | PPP |  |  | 25 |  | 27
|  |  | 0 |  | 1 |  |  |  |  | 0 | 3
|  |  | 10 |  | 11 |  |  |  |  | 22 | 25
[10 empty] | EARLIEST |  | LATEST
TASK |  | TASK NAME |  | DURATION (hrs) |  |  |  | PREDECESSOR |  | ES | EF | LS |  | LF |  | TOTAL SLACK |  |  |  |  | GANTT CHART |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39
AAA |  | login |  |  |  | 1 |  |  |  | 0 | 1 | 1 |  | 2 |  |  | 1 |  |  |  |  | AAA | bar: 0 to 1
BBB |  | sign up |  |  |  | 1 |  | A |  | 1 | 2 | 2 |  | 3 |  |  | 1 |  |  |  |  | BBB | bar: 1 to 2
CCC |  | fronts |  |  |  | 1 |  |  |  | 0 | 1 | 0 |  | 1 |  |  | 0 |  |  |  |  | CCC | bar: 0
DDD |  | Bootstraps |  |  |  | 2 |  | C |  | 1 | 3 | 1 |  | 3 |  |  | 0 |  |  |  |  | DDD | bar: 1 to 2
EEE |  | Google Front |  |  |  | 2 |  | A,B,D |  | 3 | 5 | 3 |  | 5 |  |  | 0 |  |  |  |  | EEE | bar: 3 to 4
FFF |  | padding |  |  |  | 2 |  | B,C,E |  | 5 | 7 | 5 |  | 7 |  |  | 0 |  |  |  |  | FFF | bar: 5 to 6
GGG |  | style |  |  |  | 3 |  | C,D,F, |  | 7 | 10 | 7 |  | 10 |  |  | 0 |  |  |  |  | GGG | bar: 7 to 9
HHH |  | hero section |  |  |  | 1 |  | D,G |  | 10 | 11 | 10 |  | 11 |  |  | 0 |  |  |  |  | HHH | bar: 10
III |  | navbar |  |  |  | 3 |  | E,H |  | 11 | 14 | 11 |  | 14 |  |  | 0 |  |  |  |  | III | bar: 11 to 13
JJJ |  | responsiveness |  |  |  | 2 |  | E,F,I |  | 14 | 16 | 14 |  | 16 |  |  | 0 |  |  |  |  | JJJ | bar: 14 to 15
KKK |  | padding |  |  |  | 1 |  | F,G |  | 10 | 11 | 14 |  | 15 |  |  | 4 |  |  |  |  | KKK | bar: 10 to 14
LLL |  | image |  |  |  | 1 |  | G,H,K |  | 11 | 12 | 15 |  | 16 |  |  | 4 |  |  |  |  | LLL | bar: 11 to 15
MMM |  | sizes |  |  |  | 2 |  | I,J,L |  | 16 | 18 | 16 |  | 18 |  |  | 0 |  |  |  |  | MMM | bar: 16 to 17
NNN |  | padding |  |  |  | 2 |  | J,K,M |  | 18 | 20 | 18 |  | 20 |  |  | 0 |  |  |  |  | NNN | bar: 18 to 19
OOO |  | style |  |  |  | 2 |  | K,L,N |  | 20 | 22 | 20 |  | 22 |  |  | 0 |  |  |  |  | OOO | bar: 20 to 21
PPP |  | design |  |  |  | 3 |  | L,O |  | 22 | 25 | 22 |  | 25 |  |  | 0 |  |  |  |  | PPP | bar: 22 to 24
QQQ |  | responsiveness |  |  |  | 1 |  | I,M,P |  | 25 | 26 | 25 |  | 26 |  |  | 0 |  |  |  |  | QQQ | bar: 25
RRR |  | about |  |  |  | 1 |  | M,N,Q |  | 26 | 27 | 26 |  | 27 |  |  | 0 |  |  |  |  | RRR | bar: 26
SSS |  | partnership |  |  |  | 1 |  | N,O |  | 22 | 23 | 24 |  | 25 |  |  | 2 |  |  |  |  | SSS | bar: 26 to 28
TTT |  | padding |  |  |  | 2 |  | O,P,S |  | 25 | 27 | 25 |  | 27 |  |  | 0 |  |  |  |  | TTT | bar: 29 to 30
UUU |  | testimonal |  |  |  | 1 |  | Q,R,T |  | 27 | 28 | 27 |  | 28 |  |  | 0 |  |  |  |  | UUU | bar: 31
VVV |  | take a nap |  |  |  | 1 |  | R,S,U |  | 28 | 29 | 28 |  | 29 |  |  | 0 |  |  |  |  | VVV | bar: 32
WWW |  | Bootstraps |  |  |  | 1 |  | S,T,V |  | 29 | 30 | 29 |  | 30 |  |  | 0 |  |  |  |  | WWW | bar: 33
XXX |  | row |  |  |  | 1 |  | U,V,W |  | 30 | 31 | 30 |  | 31 |  |  | 0 |  |  |  |  | XXX | bar: 34
YYY |  | footer |  |  |  | 1 |  | V,W,X |  | 31 | 32 | 31 |  | 32 |  |  | 0 |  |  |  |  | YYY | bar: 35
ZZZ |  | responsiveness |  |  |  | 7 |  | X,Y |  | 32 | 39 | 32 |  | 39 |  |  | 0 |  |  |  |  | ZZZ | bar: 33 to 39
subdivide your taks into multiple groups for having a better workload each tasks
MILESTONES |  |  | PREDECESSOR
DAY 1 (COMPLETED)
| AAA |  |  | -
| BBB |  |  | 2
DAY 2 (START)
CCC
| DDD |  |  | 4SS
TASK 2 (COMPLETED)
CCC
| DDD |  |  | 4
DAY 3 (START)
EEE
FFF
GGG
| HHH |  |  | 8SS
DAY 3 (COMPLETED)
EEE
FFF
GGG
| HHH |  |  | 8
DAY 4 (START)
III
| JJJ |  |  | 10SS
DAY 4 (COMPLETED)
III
| JJJ |  |  | 10
DAY 5 (START)
KKK
| LLL |  |  | 12SS
DAY 5 (COMPLETED)
KKK
| LLL |  |  | 12